## Risk log
Risk Register
Project name: PMO web Application
Project manager: Ashu Gupta
Risk ID | Risk description | Likelihood of the risk occurring | Impact if the risk occurs | Owner | Mitigating action | Contingent action | Progress on actions | Status | Useful resources
1 | Underestimation of design budgets and timelines. | Medium | High | Sponsor | Limiting the scope of design in the planned budget | Document the changes and exceeding budgets and notify the clients | Continuous assessment of the workflows according to the scope | Open | Busines Case /Project Charter
2 | Added workload or time requirements because of new direction, policy, or statute | Low | Medium | Project Sponsor | No ability to reduce likelihood. | Consider insurance and use Project Board to get advance notice if possible. | Project Board reviewing insurance options. | Open | Audit Plans/Internal Control Documentation
3 | Scope creep | Medium | High | Project Manager | Document the project scope in a Project Initiation Document or Project Charter and get it authorised by the Project Board. Refer to it throughout the project and assess all changes against it also ensuring alignment of any changes with the Business Case. | Document each and every example of scope creep no matter how small in a change order and get authorisation from the project board before starting work. This includes zero cost changes. | Scope clearly defined in project initation document. | Open | Project Initiation Document
4 | Lack of communication, causing lack of clarity and confusion. | Medium | Medium | Project Manager | Write a communication plan which includes frequency, goal, and audience of each communication. Identify stakeholders early and make sure they are consider the communication plan. Use most appropriate channel of communication for audience. | Correct misunderstandings immediately. Clarify areas that are not clear swiftly using assistance from Project Sponsor if needed. | Communication plan in progress. | Open | Stakeholder Identification
5 | Contractor delays | Medium | High | Project Manager | Include late penalties in contracts. Build in and protect lead time in the schedule. Communicate schedule early. Check in with suppliers regularly. Query '90% done'. Ask again and again if they need anything else. | Escalate to Project Sponsor and Contracts Manager. Implement late clauses. | Lead time from each contractor built into the project schedule. Late penalties agreed to and contracts signed. | Open | Contracts, SLA’s
6 | Unresolved project conflicts not escalated in a timely manner | Low | Medium | Project Manager | Hold regular project team meetings and look out for conflicts. Review the project plan and stakeholder engagement plan for potential areas of conflict. | When aware immediately escalate to Project Board and gain assistance from Project Sponsor to resolve the conflict. | Project team meetings scheduled. | Open | Stakeholder Management Templates
7 | Business Case becomes obsolete or is undermined by external or internal changes. | Low | High | Project Sponsor | No ability to reduce likelihood, but make sure early warning is given by reviewing business case on regular basis with the Project Board. | Initiate escalation and project close down procedure. | Project close down procedure confirmed with Project Board. SUM(Number) | Open | Busines Case Template
8 | Natural Calamities | Low | High | Project Manager | Ensure insurance in place. Familiarise project team with emergency procedures. Where cost effective put back up systems in place e.g. generators. | Notify appropriate authorities. Follow health and safety procedures. Notify stakeholders and Project Board. | Public Liability Insurance confirmed along with additional premises insurance at site B. | Open | NA
9 | Critical Resource on leave | Low | Medium | Project Manager | Backup Resource for the completion of work | Involving PMO in the role so that it helps find an asap resource for work | As and when needed meeting | Open | NA

## Severity Table
Likelihood
|  | 1 | 2 | 3
Impact | 1 | Low | Low | Medium
| 2 | Low | Medium | High
| 3 | Medium | High | High

## Dropdowns
High
Medium
Low